## PE001 - PE010
Test Case ID		PE_001	Test Case Description		Create Initial HTML Boilerplate and Commit Changes. Test on browser.
Created By		Claire Potter	Commit		commit b8bb8d9fe47d0a72fced5130d613d61f5fd7e861		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add initial boilerplate code for index.html and test that the page displays correctly. Commit changes to gitpod.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add initial boilerplate code for index.html.		Initial html boilerplate code is added to console as expected		N/A			N/A
2	Add H1 element with text Hello.		H1 element created without problems		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the page displays correctly		Page displays with the text Hello.		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_002	Test Case Description		Create CSS stylesheet and link to index.html. Test that style changes take effect.
Created By		Claire Potter	Commit		commit 33d7df14ffae041860649d9ba01062bef4a42b15		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Create CSS stylesheet and add link to index.html. Set the background colur to blue. Test that the style changes take effect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Create Assets folder.		Folder created and saved.		N/A			N/A
2	Create CSS stylesheet file in folder.		File created and saved.		N/A			N/A
3	Add link to CSS stylesheet in index.html file.		Link successfully created and saved.		N/A			N/A
4	Set page background colour to blue in stylesheet.		Add CSS code and saved.		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the page displays correctly		Page displays with the text Hello and background color blue.		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_003	Test Case Description		Create initial html symantics for index page and test that they load.
Created By		Claire Potter	Commit		commit 337909b774c61848516617d7ee380569e329fae3		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Create initial html symantics for index page- header, section and footer and test that they load.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Create Header symantics with the text header		Code entered and saved in index.html		N/A			N/A
2	Create Section symantics with the text Hero Image		Code entered and saved in index.html		N/A			N/A
3	Create Footer symantics with the text Footer.		Code entered and saved in index.html		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check that the page displays correctly		The text Header, Hero Image and Footer display.		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_004	Test Case Description		Add html code for header elements and check that the changes take effect.
Created By		Claire Potter	Commit		commit 98b5041f18ab5f3cadd2f2dbb293d76976b12cfd		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add html code for header elements - h1 and nav and check that the changes take effect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add font awesome script to html to import logo		Script added at end of file. Logo will display correctly when added.		N/A			N/A
2	Add google fonts import url to style sheet		Import added to top of sheet. Fonts will display correctly when added.		N/A			N/A
3	Add h1 element for Play Eternal logo, including link to homepage and font awesome logo.		Code entered and saved in index.html		N/A			N/A
4	Add nav symantics containing div with ul and li elements to create navigation elements. Add the li		Code entered and saved in index.html		N/A			N/A
5	Add li links with text Home, All About Sensory Play, Hear from Each Other and Contact Us.		Code entered and saved in index.html		N/A			N/A
6	Add href to link for home page as href="index.html"		Code entered and saved in index.html		N/A			N/A
7	Add default styling to css stylesheet and set the font for the body to font-family: Montserrat, sans-serif.		Code entered and saved in index.html		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check that the page displays correctly		The navigation menu displays as per input. The logo displays from font awesome. The font Montserrat displays.		As Expected			Pass
10	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
11	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_005	Test Case Description		Add style section header: ensure that all header elements - logo and nav - display as per styling.
Created By		Claire Potter	Commit		commit 2c7877d811ce1df69235377fa42ddf78d537f108		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add header styling including logo and nav menu and test that style changes take effect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add IDs to h1 and nav elements		Code entered and saved in index.html		N/A			N/A
2	Add default styling to css stylesheet.		Code entered and saved in css.stylesheet		N/A			N/A
3	Add header section to css stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
4	Add all associated styling for the header element		Code entered and saved in index.html		N/A			N/A
5	Add all associated styling for the logo ID		Code entered and saved in index.html		N/A			N/A
6	Add all associated styling for the menu ID		Code entered and saved in index.html		N/A			N/A
7	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
8	Check that the page displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
9	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
10	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_006	Test Case Description		Add link hover styling: ensure that links turn orange when hovered over.
Created By		Claire Potter	Commit		commit 7f6dece50e31df4cd7446fdb82358c6c05e76c20		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add link hover styling: ensure that links turn orange when hovered over. Add style updates to navigation menu and test effect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add a:hover color: #DD9A89;		Code entered and saved in css.stylesheet		N/A			N/A
2	Add styling updates to #menu ul		Code entered and saved in css.stylesheet		N/A			N/A
3	Add styling updates to #menu li		Code entered and saved in css.stylesheet		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check that the page displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_007	Test Case Description		Add hero image to home page and style. Add html text content. Test all changes display.
Created By		Claire Potter	Commit		commit f62cdb48de8c256412e9af6a70965128450aca47		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add hero image ensure that the correct size displays, it is not repeated, it fills the width and that the quality is high

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add html content for hero area and home page text.		Code entered and saved in index.html		N/A			N/A
2	Create images folder under assets		Folder created and saved		N/A			N/A
3	Add home-page image file to folder		Check home-page image displays.		As Expected			Pass
4	Set home-page image as background url		Code entered and saved in css.stylesheet		N/A			N/A
5	Set home-page image as background url		Code entered and saved in css.stylesheet		N/A			N/A
6	Set style for image: height, width, no-repeat and cover		Code entered and saved in css.stylesheet		N/A			N/A
7	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
8	Check that the image displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
9	Check that the home page text displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
10	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
11	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_008	Test Case Description		Home page text and text area : ensure it overlays the hero image. Ensure style loads as per code
Created By		Claire Potter	Commit		commit 7803a370e38193ec83b8b19e658a2bca5ea2a648		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Home page text and text area : ensure it overlays the hero image. Ensure style loads as per code

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add ids and classes to html.		Code entered and saved in index.html		N/A			N/A
2	Add button to home page to access about page		Folder created and saved		N/A			N/A
3	Add home-page image file to folder		Check home-page image displays.		As Expected			Pass
4	Add styling for text area in CSS		Code entered and saved in css.stylesheet		N/A			N/A
5	set positions for hero-area and hero-text.		Code entered and saved in css.stylesheet		As Expected			Pass
7	Open preview browser with python3 -m http.server		Preview browser opens and displays.		N/A			N/A
8	Check that the text area displays over the hero-area image.		Elements appear in browser as per CSS styling.		As Expected			Pass
9	Check that the home page text displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
10	Check that the button displays as per stylinh		Elements appear in browser as per CSS styling.		As Expected			Pass
11	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
12	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_009	Test Case Description		Add footer and footer styling ensure all elements appear as per code, ensure that the footer logo link opens index page, ensure that the social media icons open correct websites in new tabs.
Created By		Claire Potter	Commit		commit ed5a6904a325b32890935b80da6674f03575a856		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add footer and footer styling ensure all elements appear as per code, ensure that the footer logo link opens index page, ensure that the social media icons open correct websites in new tabs.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add footer elements to footer section		Code entered and saved in index.html		N/A			N/A
2	Add social media icons from font awesome as an unordered list with links to sites.		Code entered and saved in index.html		N/A			N/A
3	Add footer styling for all elements to stylesheet.		Code entered and saved in css.stylesheet		N/A			N/A
4	Add styling for text area in CSS		Code entered and saved in css.stylesheet		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the footer area displays as expected.		Elements appear in browser as per CSS styling.		As Expected			Pass
7	Check that the facebook icon opens the link to facebook in a new tab.		Facebook opens as per link in a new tab.		As Expected			Pass
8	Check that the instagram icon opens the link to instagram in a new tab.		Instagram opens as per link in a new tab.		As Expected			Pass
9	Check that the twitter icon opens the link to twitter in a new tab.		Twitter opens as per link in a new tab.		As Expected			Pass
10	Check that the Play Eternal footer logo link opens index.html		Link directs to correct page		As Expected			Pass
11	*Amendment* Add changes to home page button styling for display purposes.		Code entered and saved in css.stylesheet		Amendment to previous home page elements added through previous commit.			N/A
12	*Amendment* Add changes to home page elements in html for display purposes		Code entered and saved in index.html		Amendment to previous home page elements added through previous commit.			N/A
13	Check that the home page text displays correctly and the button aligns correctly.		Happy with display in preview.		As Expected			Pass

Test Case ID		PE_010	Test Case Description		Create about, contact and feedback pages. Ensure that the header and footer load consistently across pages. Ensure that links on all pages to about, feedback and contact pages all work and open correctly.
Created By		Claire Potter	Commit		commit ed5a6904a325b32890935b80da6674f03575a856		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Create about, contact and feedback pages. Ensure that the header and footer load consistently across pages. Ensure that links on all pages to about, feedback and contact pages all work and open correctly.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Create about.html file. Copy header and footer from index.html to new page.		html file created successfully with header and footer duplicated from index.html		N/A			N/A
2	Create feedback.html file. Copy header and footer from index.html to new page.		html file created successfully with header and footer duplicated from index.html		N/A			N/A
3	Create contact.html file. Copy header and footer from index.html to new page.		html file created successfully with header and footer duplicated from index.html		N/A			N/A
4	Add page links to navigation in header across all pages.		Each link has correct page href added.		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the about.html page loads		Page opens and all elements display.		As Expected			Pass
7	Check that the feedback.html page loads		Page opens and all elements display.		As Expected			Pass
8	Check that the contact.html page loads		Page opens and all elements display.		As Expected			Pass
9	from index.html check that all navigation links direct to correct page.		Navigated to the correct pages.		As Expected			Pass
10	from about.html check that all navigation links direct to correct page.		Navigated to the correct pages.		As Expected			Pass
11	from feedback.html check that all navigation links direct to correct page.		Navigated to the correct pages.		As Expected			Pass
12	from contact.html check that all navigation links direct to correct page.		Navigated to the correct pages.		As Expected			Pass
13	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
14	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## PE011 - PE020
Test Case ID		PE_011	Test Case Description		Add shadow to button on home page. Ensure it shows when hover over button. Ensure button link opens about page.
Created By		Claire Potter	Commit		commit 3b15595cf7b736876e289a11c751dc7888e5ea1f		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	CSS stylesheet preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add shadow to button on home page. Ensure it shows when hover over button. Ensure button link opens about page. Shadow code from W3 school tutorials.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Adjust styling for the button to round the edges and increase padding.		Code entered and saved in css.stylesheet		N/A			N/A
2	Add the shadow styling code to the css.stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the style changes to the button display correctly.		Button appears rounded with more padding. Button is longer and placed closer to text.		As Expected			Pass
5	Hover over the button and check that the shadow appears.		Shadow shows when hovering over the button.		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_012	Test Case Description		Add dropdown menu to navigation for about page and test that the updates pull through across screens.
Created By		Claire Potter	Commit		commit b6190871f9e5fad944e26daf57091248db321c94		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add dropdown menu to navigation for about page and test that the updates pull through across screens. - Dropdown from W3 school tutorial for dropdown menu - adjusted for this site / https://www.w3schools.com/css/tryit.asp?filename=trycss_dropdown_navbar.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add dropdown menu code to about.html		Code entered and saved in about.html		N/A			N/A
2	Add a sub-menu area with page links code in addition to about.html		Code entered and saved in about.html		N/A			N/A
3	Copy dropdown menu code to nav section in index.html		Code entered and saved in index.html		N/A			N/A
4	Copy dropdown menu code to nav section in feedback.html		Code entered and saved in feedback.html		N/A			N/A
5	Copy dropdown menu code to nav section in contact.html		Code entered and saved in contact.html		N/A			N/A
6	Add dropdown styling to css stylesheet.		Code entered and saved in css.stylesheet		N/A			N/A
7	Add link to about.html to Learn More button on home page		index.html		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check that the dropdown menu displays on index.html		Menu displays when hovered over and menu items display correctly		As Expected			Pass
10	Check that the learn-more button link opens the about.html page		correct page opens when link is followed.		As Expected			Pass
11	Check that the dropdown menu displays on about.html		Menu displays when hovered over and menu items display correctly		As Expected			Pass
12	Check that the sub-area menu displays on about.html		Menu displays as an additional sub menu on about.html		As Expected			Pass
13	Check that the dropdown menu displays on feedback.html		Menu displays when hovered over and menu items display correctly		As Expected			Pass
14	Check that the dropdown menu displays on contact.html		Menu displays when hovered over and menu items display correctly		As Expected			Pass
15	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
16	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_013	Test Case Description		Test that What is Sensory Play loads correctly with correct styling
Created By		Claire Potter	Commit		commit b6bba6e93a45508f681f2364055e8ab4b394dbce		Version		1.0

Tester's Name		Claire Potter	Date Tested		08-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Test that What is Sensory Play loads correctly with correct styling. Test that page reference links work correctly.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add What is Sensory Play section code to about.html		Code entered and saved in about.html		N/A			N/A
2	Add section headers for Play in Motion, Activities and Help with Anxiety Sections		Code entered and saved in about.html		N/A			N/A
3	Add ids to sections and create href links for the sections in the dropdown menu		Code entered and saved in about.html		N/A			N/A
4	Add ids to sections and create href links for the sections in the sub-menu of about.html		Code entered and saved in about.html		N/A			N/A
5	Add styling for What is Sensory Play and about.html to the CSS stylesheet.		Code entered and saved in css.stylesheet		N/A			N/A
6	Copy dropdown with hrefs code and add to index.html nav		Code entered and saved in index.html		N/A			N/A
7	Copy dropdown with hrefs code and add to feedback.html nav		Code entered and saved in feedback.html		N/A			N/A
8	Copy dropdown with hrefs code and add to contact.html nav		Code entered and saved in contact.html		N/A			N/A
9	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
10	Check that the about.html page loads correct with styling		Header, Footer and What is Sensory Play page load correctly and styling reflects as expected.		As Expected			Pass
11	Check that the page links work from the dropdown menu and the sub-menu		Links lead to correct page section.		As Expected			Pass
12	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
13	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_014	Test Case Description		Test Play in Motion iframe video play correctly
Created By		Claire Potter	Commit		commit 98655ce63a6805d610df99f215860426550a426c		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Test Play in Motion iframe video play correctly

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add iframe code from you tube to about.html		Code entered and saved in index.html		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check that the video display correctly, including controls, check that it plays.		Video plays directly from site when prompted by the user.		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_015	Test Case Description		Restyle nav dropdown menu to inline block and re-order menu items, check it displays correctly.
Created By		Claire Potter	Commit		commit 98655ce63a6805d610df99f215860426550a426c		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add header styling including logo and nav menu and test that style changes take effect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Change dropdown display to inline block in CSS sheet		Code entered and saved in css.stylesheet		N/A			N/A
2	Re-order menu items on about.html		Code entered and saved in about.html		N/A			N/A
3	Re-order menu items on feedback.html		Code entered and saved in feedback.html		N/A			N/A
4	Re-order menu items on contact.html		Code entered and saved in contact.html		N/A			N/A
5	Re-order menu items on index.html		Code entered and saved in index.html		N/A			N/A
6	Use Cntrl Alt F to format about.html		about.html format is edited to be neat		N/A			N/A
7	Ue Cntrl Alt F to format css.stylesheet		about.html format is edited to be neat		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check that the menu items appear in correct order across all pages		Menu items appear in correct order.		As Expected			Pass
10	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
11	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_016	Test Case Description		Test Activities section loads correctly and with correct styling on about.html page
Created By		Claire Potter	Commit		commit d88968065547e63e2e0a52bcb191417e408ad93d		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Test Activities section loads correctly and with correct styling on about.html page.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add activities content code to about.html - Activities section		Code entered and saved in about.html		N/A			N/A
2	Add activities styling to css.stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the page displays correctly		Elements appear in browser as per CSS styling.		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_017	Test Case Description		Test Help with Anxiety loads correctly and with correct styling on about.html page
Created By		Claire Potter	Commit		commit d317b3a413d340a33ae74499a4f3ac9d85144f6c		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Test Help with Anxiety loads correctly and with correct styling on about.html page

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add html content for help with anxiety section		Code entered and saved in index.html		N/A			N/A
2	Add styling for Help with Anxiety section to css.stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the Help with Anxiety section displays with correct content and styling		Content and styling appear as expected		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_018	Test Case Description		Remove styling from iframe in about.html and add to stylesheet. Check in preview.
Created By		Claire Potter	Commit		commit 97fd4f7fcc7e6103cff78b88cbf8f5bb4fd501a5		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Remove styling from iframe in about.html and add to stylesheet. Check in preview.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove styling from iframe in about.html		Code removed from about.html		N/A			N/A
2	Add styling for iframe to css.stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the video displays correctly and plays		Elements appear in browser as per CSS styling and plays.		As Expected			Pass

Test Case ID		PE_019	Test Case Description		Add tooltips to Help with Anxiety section and test they work.
Created By		Claire Potter	Commit		commit 97fd4f7fcc7e6103cff78b88cbf8f5bb4fd501a5		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add tooltips to Help with Anxiety section and test that they work. Code from W3 schools tutorial on Tooltips / https://www.w3schools.com/css/tryit.asp?filename=trycss_tooltip_arrow_bottom

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add tooltip classes to about.html Help with Anxiety		Code entered and saved in about.html		N/A			N/A
2	Add tooltip styling to css.stylesheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the tooltips display as expected on hover on about.html		Tooltips display as expected		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_020	Test Case Description		Add back to top buttons to about.html sections and test that it works
Created By		Claire Potter	Commit		commit 47571ec70dbcb343ed55d024910e581832a24f87		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add back to top buttons to about.html sections and test that it works

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add back to top buttons to each page section on about.html page		Code entered and saved in about.html		N/A			N/A
2	Add button styling to css.stylesheet for back to top buttons		Code entered and saved in css.stylesheet		N/A			N/A
3	Use Cntrl Alt F to format about.html		about.html page is neatly formatted		N/A			N/A
4	Use Cntrl Alt F to format css.stylesheet		css.stylesheet page is neatly formatted		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that each back to top button returns the user to the top of the page		Directed to top of page by the button		As Expected			Pass
7	Check that all of the buttons appear as per styling		Elements appear in browser as per CSS styling		As Expected			Pass
8	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
9	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## PE021 - PE030
Test Case ID		PE_021	Test Case Description		Add sticky position to header when scrolling and javascript and test.
Created By		Claire Potter	Commit		commit 12e7e077276b7692a748c61b3d47041c8ffd31f0		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass/Fail/Not Executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add sticky position to header when scrolling and javascript and test. Javascript from W3 school tutorial for sticky nav bar and adjusted for this site / https://www.w3schools.com/howto/tryit.asp?filename=tryhow_js_navbar_sticky.

Step #	Step Details		Expected Results		Actual Results			Pass/Fail/Not Executed

1	Add style code for sticky header and content to stylesheet.css		Code entered and saved in css.stylesheet		N/A			N/A
2	Make amendments to header and nav existing styling to improve as well as fit the sticky header.		Code entered and saved in css.stylesheet		N/A			N/A
3	Remove the styling for the back to top buttons as no longer required with sticky header		Code entered and saved in css.stylesheet		N/A			N/A
4	Add will change: transform to elements to improve performance when rendering on different screens		Code entered and saved in css.stylesheet		N/A			N/A
5	Add javascript reference to navigation code on index.html, about.html, feedback.html and contact.html		Code entered and saved in html pages		N/A			N/A
6	Format about.html using Cntrl Alt F to ensure neat formatting		about.html code looks neat and formatted		N/A			N/A
7	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
8	Check that the header sticks when scrolling on all pages		Header stays fixed when scrolling down the page		As Expected			Pass
9	Check that the content can be seen and that the page scrolls smoothly		Shadow shows when hovering over the button.		Passed but there can be some improvement made to display.			Pass
10	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
11	Commit the code to gitpod.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_022	Test Case Description		Add z-index to relative and absolute positions and test
Created By		Claire Potter	Commit		commit c041ac53bb859fcc9bf2266275fff3555794efde		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add z-index to relative and absolute positions and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Create ID for button - learn-more on index.html		Code entered and saved in index.html		N/A			N/A
2	Add z-index to elements with the position created to make sure that they fall behind the sticky header when scrolling.		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that positioned elements on index page and about page fall behind the sticky header when scrolling and not on top.		When scrolling down the page all elements fall behind the header and do not go over the top.		As Expected			Pass
5	Check that the learn-more button link opens the about.html page		Click the button and the page opens		The link will not activate			Fail - Fail for now to be corrected when resolved
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_023	Test Case Description		Renames classes and IDs where _ was used to - for consistency - ensure all style settings till reflect.
Created By		Claire Potter	Commit		commit df886c25c399ca0f0c7f09096487f1d80e6a41c5		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass/Fail/Not Executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Renames classes and IDs where _ was used to - for consistency - ensure all style settings till reflect.

Step #	Step Details		Expected Results		Actual Results			Pass/Fail/Not Executed

1	Renames classes and IDs where _ was used to - for consistency		Code entered and saved in about.html		N/A			N/A
2	Renames classes and IDs where _ was used to - for consistency		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the about.html page loads correct with styling		Check that all styling still reflects correctly with name changes		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_024	Test Case Description		Add max-width: 850px media query for Header and Navigation. Test display on screen size.
Created By		Claire Potter	Commit		commit 84b7c05ea8b052fd73fabf75a74fbde8be66a63f		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	contact.html preview
4					4	feedback.html preview

Test Scenario	Add max-width: 850px media query for Header and Navigation. Test display on screen size.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add max-width 850 @media query styling to stylesheet		Add code to css.stylesheet		N/A			N/A
2	Format index.html using Cntrl Alt F to ensure neat formatting		index.html code looks neat and formatted		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the header and navigation displays neatly for screen size max width 850		Header and navigation displays correctly and neatly for screen width		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_025	Test Case Description		Add media queries for various screen sizes for index.html - Home Page and test
Created By		Claire Potter	Commit		commit 9bf4978ce94a0e416ddd5bfc606f1cad211a8450		Version		1.0

Tester's Name		Claire Potter	Date Tested		09-May-21		Pass/Fail/Not Executed		Fail

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add media queries for various screen sizes for index.html - Home Page and test

Step #	Step Details		Expected Results		Actual Results			Pass/Fail/Not Executed

1	Change max-width 850 to max-width 1090 on exisiting media query		Code entered and saved in css.stylesheet		N/A			N/A
2	Add @media screen and max-width 900px query		Code entered and saved in css.stylesheet		N/A			N/A
3	Add @media screen and max-width 740px query		Code entered and saved in css.stylesheet		N/A			N/A
4	Add @media screen and max-width 550px query		Code entered and saved in css.stylesheet		N/A			N/A
5	Add @media screen and max-width 380px query		Code entered and saved in css.stylesheet		N/A			N/A
6	Add @media screen and max-width 250px query		Code entered and saved in css.stylesheet		N/A			N/A
7	Ue Cntrl Alt F to format css.stylesheet		formatted to display neat		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check that the home page - index.html displays correctly for max-width 1090 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
10	Check that the home page - index.html displays correctly for max-width 900 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
11	Check that the home page - index.html displays correctly for max-width 740 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
12	Check that the home page - index.html displays correctly for max-width 550 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
13	Check that the home page - index.html displays correctly for max-width 380 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
14	Check that the home page - index.html displays correctly for max-width 250 screen		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
10	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
11	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_026	Test Case Description		Amend index.html code to improve default display as well as @media queries. Test display across screen sizes.
Created By		Claire Potter	Commit		commit 9e12d8e4fa31a4f03e3524c1205d3ee65910e617		Version		1.0

Tester's Name		Claire Potter	Date Tested		10-May-21		Pass / Fail / Not executed		Fail

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Amend index.html code to improve default display as well as @media queries. Test display across screen sizes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Amend default styling for the header, home-page and footer to improve overall display		Code entered and saved in css.stylesheet		N/A			N/A
2	Update z-index for header and learn-more button to try to get the link to work		Code entered and saved in css.stylesheet		N/A			N/A
3	Update styling for media query screen size max 1090px		Code entered and saved in css.stylesheet		N/A			N/A
4	Update styling for media query screen size max 740px		Code entered and saved in css.stylesheet		N/A			N/A
5	Update styling for media query screen size max 550px		Code entered and saved in css.stylesheet		N/A			N/A
6	Update styling for media query screen size max 380px		Code entered and saved in css.stylesheet		N/A			N/A
7	Change max-width from 250px to 292px and update styling.		Code entered and saved in css.stylesheet		N/A			N/A
8	Add styling for max-width 229px		Code entered and saved in css.stylesheet		N/A			N/A
9	Add styling for max-width 170px		Code entered and saved in css.stylesheet		N/A			N/A
10	Add styling for max-width 163px		Code entered and saved in css.stylesheet		N/A			N/A
11	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
12	Check that the default screen display of the index.html page displays correctly		All page elements display correctly and look neat and readable		As Expected			Pass
13	Check that the display of the index.html page displays correctly for screen-size 1090px max		All page elements display correctly and look neat and readable		Improved since previous commit but not 100%			Fail
14	Check that the display of the index.html page displays correctly for screen-size 740px max		All page elements display correctly and look neat and readable		Improved since previous commit but not 100%			Fail
15	Check that the display of the index.html page displays correctly for screen-size 550px max		All page elements display correctly and look neat and readable		Improved since previous commit but not 100%			Fail
16	Check that the display of the index.html page displays correctly for screen-size 380px max		All page elements display correctly and look neat and readable		Improved since previous commit but not 100%			Fail
17	Check that the display of the index.html page displays correctly for screen-size 292px max		All page elements display correctly and look neat and readable		Improved since previous commit but not 100%			Fail
18	Check that the display of the index.html page displays correctly for screen-size 229px max		All page elements display correctly and look neat and readable		Looks fine but not 100%			Fail
19	Check that the display of the index.html page displays correctly for screen-size 170px max		All page elements display correctly and look neat and readable		Looks fine but not 100%			Fail
20	Check that the display of the index.html page displays correctly for screen-size 163px max		All page elements display correctly and look neat and readable		Looks fine but not 100%			Fail
21	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
22	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_27	Test Case Description		Consolidate styling into one class, test style still loads correctly
Created By		Claire Potter	Commit		commit b1db9f55225235eaf45610f1b997044a005bf454		Version		1.0

Tester's Name		Claire Potter	Date Tested		10-May-21		Pass/Fail/Not Executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Consolidate styling into one class, test style still loads correctly

Step #	Step Details		Expected Results		Actual Results			Pass/Fail/Not Executed

1	Add html class to sections to consolidate styling class		Code entered and saved in index.html		N/A			N/A
2	Add .solid background class and remove styles across classes to consolidate styling for ease of maintenance		Code entered and saved in css.stylesheet		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check the About.html page to ensure that style still loads as expected after consolidation.		Styling appear as expected		As Expected			Pass

Test Case ID		PE_028	Test Case Description		Add media queries with styling for about.html and test. Make amendments to media queries for index.html and test.
Created By		Claire Potter	Commit		commit b1db9f55225235eaf45610f1b997044a005bf454		Version		1.0

Tester's Name		Claire Potter	Date Tested		10-May-21		Pass / Fail / Not executed		Fail

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add media queries with styling for about.html and test. Make amendments to media queries for index.html and test.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add media query for screen width max 970px for about.html		Code entered and saved in css.stylesheet		N/A			N/A
2	Add media query for screen width max 870px for about.html		Code entered and saved in css.stylesheet		N/A			N/A
3	Add media query for screen width max 770px for about.html		Code entered and saved in css.stylesheet		N/A			N/A
4	Amend media query for max width 900px for index.html page		Code entered and saved in css.stylesheet		N/A			N/A
5	Amend media query for max width 740px for index.html page		Code entered and saved in css.stylesheet		N/A			N/A
6	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
7	Check that the style loads correctly for about.html max-screen 970px		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
8	Check that the style loads correctly for about.html max-screen 870px		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
9	Check that the style loads correctly for about.html max-screen 770px		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
10	Check that the style loads correctly for index.html max-screen 900px		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
11	Check that the style loads correctly for index.html max-screen 740px		All page elements display correctly and look neat and readable		Improvements can be made to code to improve display			Fail
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_029	Test Case Description		Check code on W3C HTML and make amendments to pass. Once passed check preview for site.
Created By		Claire Potter	Commit		commit 8dea70c08a5ceac8e0bd9a9a3ae3715e9254dc8e		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass/Fail/Not Executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Check code on W3C HTML and make amendments to pass. Once passed check preview for site.

Step #	Step Details		Expected Results		Actual Results			Pass/Fail/Not Executed

1	Received html code error that the following href appeared more than once href="javascript:void(0)"		The following href should only appear once href="javascript:void(0)"		I had added the code multiple times to occur with every menu item in the navigation as well as with the home page links in the logos.			Fail
2	Removed duplicated href href="javascript:void(0)" so that it only remains once per page to trigger javascript		The following href should only appear once href="javascript:void(0)"		As Expected			Pass
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that the Header and Navigation on index.html display and work correctly		Header and Navigation display and are fixed. Dropdown menu works		As Expected			Pass
5	Check that the Header and Navigation on about.html display and work correctly		Header and Navigation display and are fixed. Dropdown menu works		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

Test Case ID		PE_030	Test Case Description		Amend classes and ids to consolidate styling for maintenance purposes. Test all changes
Created By		Claire Potter	Commit		commit 8dea70c08a5ceac8e0bd9a9a3ae3715e9254dc8e		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Amend classes and ids to consolidate styling for maintenance purposes. Test all changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Change content class to id as it is only used once		Code entered and saved in about.html		N/A			N/A
2	Remove top ID from about.html as back to top buttons have been removed		Code entered and saved in about.html		N/A			N/A
3	Add class=senses_info across about.html sections		Code entered and saved in about.html		N/A			N/A
4	Remove class grid-figure from about.html as it is not utilised		Code entered and saved in about.html		N/A			N/A
5	Create .senses_info to consolidate styling for maintenance purposes		Code entered and saved in stylesheet.css		N/A			N/A
6	Remove duplicated styling from other classes		Code entered and saved in stylesheet.css		N/A			N/A
7	Add senses_info class to media queries to adjust display size		Code entered and saved in stylesheet.css		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check about.html page to ensure all styling is pulling through correctly after changes		Page styling appears as expected		As Expected			Pass
10	Check screen sizes to ensure that the display change for senses_info reflects		Check on different screen sizes		As Expected			Pass

## PE031-PE040
Test Case ID		PE_031	Test Case Description		Amend fixed header and media queries to improve display. Test all changes
Created By		Claire Potter	Commit		commit 8dea70c08a5ceac8e0bd9a9a3ae3715e9254dc8e		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Amend fixed header and media queries to improve display. Test all changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Increase padding for sticky-content to ensure there is enough space before content for smaller screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
2	Add sticky-content padding to media queries to ensure content is visible under the fixed header across media sizes.		Code entered and saved in stylesheet.css		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Test page loading across different screen sizes to make sure there is enough space between the fixed header and the content		There is adequate spacing and all content is readable before and after scrolling		As Expected			Pass
Test Case ID		PE_032	Test Case Description		Make fixes across index and about pages to improve display and style
Created By		Claire Potter	Commit		commit 8dea70c08a5ceac8e0bd9a9a3ae3715e9254dc8e		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Make fixes across index and about pages to improve display and style

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Change heading from h1 to h2 as there should only be one h1 per page		Code entered and saved in about.html		N/A			N/A
2	Use Cntrl Alt F to format about.html neatly		about.html appears neat and well formatted		N/A			N/A
3	Adjust learn-more font-size and weight to increase readability		Code entered and saved in stylesheet.css		N/A			N/A
4	Adjust about menu h2 so that it centers		Code entered and saved in stylesheet.css		N/A			N/A
5	Add border to iframe styling for spacing purposes for display		Code entered and saved in stylesheet.css		N/A			N/A
6	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
7	Check the effect of the style changes across the index.html and about.html pages		Pages display with styling as expected		As Expected			Pass
8	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
9	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_033	Test Case Description		Change class name and split class in to two for different styling purposes. Test all changes.
Created By		Claire Potter	Commit		commit d4231ce2f80c242b53877c97b43d005a6ad389d8		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Change class name and split class in to two for different styling purposes. Test all changes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Change id=content to id=page-content for purpose clarity		Code entered and saved in about.html and index.html and stylesheet.css		N/A			N/A
2	Split senses_info into senses-info-right and senses-info-left t be able to differentiate style for right aligned and left aligned.		Code entered and saved in stylesheet.css. Class names changed in about.html		N/A			N/A
3	Add name changes and split class to @media queries to ensure they align.		Code entered and saved in stylesheet.css.		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check about.html and index.html to ensure that the changes have not affected the styling		The style of the about.html and index.html pages reflects as expected		As Expected			Pass
Test Case ID		PE_034	Test Case Description		Add remaining @media queries for about page, save and test.
Created By		Claire Potter	Commit		commit d4231ce2f80c242b53877c97b43d005a6ad389d8		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Fail

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add remaining @media queries for about page, save and test.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add changes to 770px media query for about.html page elements		Code entered and saved in stylesheet.css		N/A			N/A
2	Add media query for screen size max 670px for about.html		Code entered and saved in stylesheet.css		N/A			N/A
3	Remove @media screen and (max-width: 550px) as no longer needed		Code removed and saved in stylesheet.css		N/A			N/A
4	Add media query for @media screen and (max-width: 560px)		Code entered and saved in stylesheet.css		N/A			N/A
5	Add media query for @media screen and (max-width: 480px)		Code entered and saved in stylesheet.css		N/A			N/A
6	Add media query for @media screen and (max-width: 380px)		Code entered and saved in stylesheet.css		N/A			N/A
7	Add media query for @media screen and (max-width: 292px)		Code entered and saved in stylesheet.css		N/A			N/A
8	Add media query for @media screen and (max-width: 255px)		Code entered and saved in stylesheet.css		N/A			N/A
9	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
10	Check screen size max 770px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
11	Check screen size max 670px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
12	Check screen size max 560px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
13	Check screen size max 480px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
14	Check screen size max 380px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
15	Check screen size max 292px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
16	Check screen size max 255px to ensure style changes have taken effect.		Page displays neat and well styled for screen size		Improvements can be made to code to improve display			Fail
17	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
18	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_035	Test Case Description		Fix formatting across CSS stylesheet for consistency. Check changes reflect.
Created By		Claire Potter	Commit		commit 20d9f03c739f511ed23b0dfa1e8ae35636efb1ba		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Fix formatting across CSS stylesheet for consistency. Check changes reflect.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove class="senses-info-right" from the Taste heading as it is not required		Code removed and saved in stylesheet.css		N/A			N/A
2	Change comments headings to have capital letters for readability		Code entered and saved in stylesheet.css		N/A			N/A
3	Remove page-content and sticky page-content classes to remove the padding from the pages.		Code removed and saved in stylesheet.css		N/A			N/A
4	Move Classes Used Across Page section to under About Page for readability of CSS code.		Code moved and saved in stylesheet.css		N/A			N/A
5	Ensure changes reflect across @media queries for consistency		Code changed and saved in stylesheet.css		N/A			N/A
6	Use Cntrl Alt F to format stylesheet.css neatly		code appears well formatted and neat		N/A			N/A
7	Remove the duplicated href="javascript:void(0)" from the navigation on contact.html		duplicated href is removed and only reflects once in the page		N/A			N/A
8	Change the h1 heading to an h2 so that an h1 only appears once on the contact.html page		only one h1 element per page		N/A			N/A
9	Remove the content class div from the contact page		code removed and saved in contact.html		N/A			N/A
10	Remove the duplicated href="javascript:void(0)" from the navigation on feedback.html		duplicated href is removed and only reflects once in the page		N/A			N/A
11	Change the h1 heading to an h2 so that an h1 only appears once on the feedback.html page		only one h1 element per page		N/A			N/A
12	Remove the content class div from the feedback page		code removed and saved in feedback.html		N/A			N/A
13	Remove the page-content class div from the index.html		code removed and saved in index.html		N/A			N/A
14	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
15	Check that the Taste heading style reflects as required on the contact.html page		CSS style reflects as required on the contact.html page		As Expected			Pass
16	Check that the links on pages below the header and navigation work now that the content, page-content and sticky classes have been removed from pages		Links work when clicked		Did not work			Fail
17	Check that the header and navigation is fixed and that the dropdown works with the duplicate hrefs removed		Header is fixed and sub-menu displays		As Expected			Pass
18	Check that the Headings reflect correctly after being changed from an h1 to a h2		Heading reflects as expected with h2 styling		As Expected			Pass
19	Check that all style for the about.html pages reflects as expected after moving the code section		style reflects as expected		As Expected			Pass
20	Check that the changes made, reflect to the media queries as it does on the default		style reflects as expected		As Expected			Pass
21	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
22	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_036	Test Case Description		Add Hear From Each Other section and styling and test changes
Created By		Claire Potter	Commit		commit 7109109d564d5bdca20a2a65fbc333619dcef7fe		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add Hear From Each Other section and styling and test changes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add Hear From Each Other section code to feedback.html		Code entered and saved in feedback.html		N/A			N/A
2	Add Hear From Each Other style section to the style sheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Fix the navigation and heading on the contact.html page		Code entered and saved in contact.html		N/A			N/A
4	Add contact us heading style section to the style sheet		Code entered and saved in css.stylesheet		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the Hear From Each Other Contact reflects correctly		check text and content appears as expected		As Expected			Pass
7	Check that the Contact Us page navigation works correctly		Navigation leads to correct pages		As Expected			Pass
8	Check that the Contact Us heading reflects as per styling		Style reflects as expected		As Expected			Pass
9	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
10	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_037	Test Case Description		Add content div to improve scrolling and padding for fixed header. Test changes reflect
Created By		Claire Potter	Commit		commit 9c486c3e4b489b242ce345790a4517ea6a2c1ab1		Version		1.0

Tester's Name		Claire Potter	Date Tested		11-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Add content div to improve scrolling and padding for fixed header. Test changes reflect

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add back the content div to the index, about, feedback and contact pages to add the padding back and improve scrolling with the fixed header		Update code across html pages		N/A			N/A
2	Add back the content and sticky + content classes to the stylesheet and style		Code entered and saved in stylesheet.css		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check across all pages that the padding now reflects when the page opens and when scrolling		There is adequate spacing and all content is readable before and after scrolling		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_038	Test Case Description		Add Contact page html and style. Test changes
Created By		Claire Potter	Commit		commit 291cfb22a8ccdea40d2e3ea169b80bf6dd42008d		Version		1.0

Tester's Name		Claire Potter	Date Tested		12-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4

Test Scenario	Add Contact page html and style. Test changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add Get In Touch section code to contact.html		Code entered and saved in contact.html		N/A			N/A
2	Add Get In Touch style section to the style sheet		Code entered and saved in css.stylesheet		N/A			N/A
3	Make small adjustments to hero-area css to update display		Code entered and saved in css.stylesheet		N/A			N/A
4	Make small adjustments to feedback heading css to update display		Code entered and saved in css.stylesheet		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the Get In Touch page reflects correctly		check text and content appears as expected		As Expected			Pass
7	Check that the styling of the Get In Touch page is as expected		Style reflects as expected		As Expected			Pass
8	Check that the small adjustments to the hero-area and the feedback heading improves the spacing of the pages		Style reflects as expected		As Expected			Pass
9	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
10	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_039	Test Case Description		Amend fixed header and media queries to improve display. Test all changes
Created By		Claire Potter	Commit		commit 802b11e96b2e351629c061c98c28b69fb4c36514		Version		1.0

Tester's Name		Claire Potter	Date Tested		12-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	feedback.html preview
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Check code and correct small miss-types

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	On contact.html make sure that all classes and ID names are captured correctly, remove unnecessary <br> code and ensure all form imput and labels match as per the fields required		Code entered and saved in contact.html		N/A			N/A
2	change the feed-sub id to a class in feedback.html and stylesheet		Code entered and saved in stylesheet.css and feedback.html		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check that all content and styling on the contact.us page reflects as expected		All content and styling reflects as wanted		As Expected			Pass
5	Check that the feed-sub styling is pulling through to the right section		All content and styling reflects as wanted		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_040	Test Case Description		Update sticky nav bar and remove sub-menu. Test all changes
Created By		Claire Potter	Commit		commit 1ea255c40e92c6e9b7794229334b3bbf4f2e7ffc		Version		1.0

Tester's Name		Claire Potter	Date Tested		12-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html
4					4	contact.html

Test Scenario	Update sticky nav bar and remove sub-menu. Test all changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove sub-navigation section from about page as it is unnecessary with sticky nav bar		Code removed and saved in about.html		N/A			N/A
2	Remove sub-menu styling		Code entered and saved in stylesheet.css		N/A			N/A
3	Add scroll-behavior: smooth to html style to improve smoothness of scrolling		Code entered and saved in stylesheet.css		N/A			N/A
4	Remove z-index from hero area and hero text and learn-more to get the link to work for the button		Code entered and saved in stylesheet.css		N/A			N/A
5	Add min-height 300px for sticky nav		Code entered and saved in stylesheet.css		N/A			N/A
6	Update padding and learn more button position across all screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
7	Remove sticky nav bar from index, contact and feedback pages so that all links can work. Only remains on about page		Code removed from index.html, feedback.html and contact.html		N/A			N/A
8	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
9	Check that the sub-menu does not appear on about.html		Page displays without the sub-menu		As Expected			Pass
10	Check that the scrolling behavour for the sticky nav bar is smooth, there is ennough padding on about.html		Sticky nav is present on about.html and page scrolls smoothly		As Expected			Pass
11	Check that the learn-more button displays according to new styling in the hero-text section. Check that the navigation does not stick on index.html		Sticky nav is not present on index.html, the learn-more link works		As Expected			Pass
12	Check the positiing of the learn-more button across different screen sizes		positioned as per styling		As Expected			Pass
13	Check that the nav bar does not stick on feedback.html or contact.html. Check that all inputs and submit button works		All content works as expected. Nav bar does not stick.		As Expected			Pass
14	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
15	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## PE041 - PE050
Test Case ID		PE_041	Test Case Description		Add media query changes to style sheet and test all changes
Created By		Claire Potter	Commit		commit 5742144b66600d06fd6c27adb55da69fd389e52c		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Fail

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add media query changes to style sheet and test all changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove min-height requirement for sticky nav		Code removed and saved in stylesheet.css		N/A			N/A
2	Adjust height and width for elements to fit-content		Code entered and saved in stylesheet.css		N/A			N/A
3	Add a small image for home page hero-area for smaller screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Test display across pages across various screen sizes to check that it has improved with changes.		Changes have improved display across screen sizes		Improved but not where it needs to be as yet			Fail
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_042	Test Case Description		Add format changes to header footer, nav and page contents to improve site performance. Test all changes.
Created By		Claire Potter	Commit		commit ef5c03c2a9d1abcaa9813d8372ee297c2f21a1f4		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	contact.html preview
4					4	feedback.html preview

Test Scenario	Add format changes to header footer, nav and page contents to improve site performance. Test all changes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add a div with ID play-images to top 10 activities images to be able to format them easily across screen sizes		Code entered and saved in about.html		N/A			N/A
2	Add position: relative to the html styling to position elements to the html		Code entered and saved in stylesheet.css		N/A			N/A
3	Change header display to flex, flex row and remove float so that it is easier to style across media queries		Code entered and saved in stylesheet.css		N/A			N/A
4	Change navigation display to flex		Code entered and saved in stylesheet.css		N/A			N/A
5	Update sticky nav and content padding for fixed header		Code entered and saved in stylesheet.css		N/A			N/A
6	Set the footer as fixed and absolute to the relative htiml		Code entered and saved in stylesheet.css		N/A			N/A
7	Update z-index across elements and remove will transform		Code entered and saved in stylesheet.css		N/A			N/A
8	Update top 10 activities and play images to display as flex and set flex direction		Code entered and saved in stylesheet.css		N/A			N/A
9	Update the width and height to fit-content for various elements		Code entered and saved in stylesheet.css		N/A			N/A
10	Update font-sizes for various elements across screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
11	Update various media queries max width to improve display across screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
12	Remove colons from contact.html form labels		Code entered and saved in contact.html		N/A			N/A
13	Add back sticky nav to contact.html, index.html and feedback.html		Code entered and saved in contact.html index.html and feedback.html		N/A			N/A
14	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
15	Check the effect of the style changes across the about.html page		Pages display with styling as expected		As Expected			Pass
16	Check the fixed footer across all pages		Footer is now fixed		As Expected			Pass
17	Check the changes to the header and navigation dispaly across all pages		Header displays as expected		As Expected			Pass
18	Check that the sticky nav bar is now active and working across all pages		Header and nav stick as the page is scrolled		As Expected			Pass
19	Check the format changes to the contact.html page have taken effect		Formatted as expected		As Expected			Pass
20	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
21	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_043	Test Case Description		Add layout changes to menu to improve display. Test changes.
Created By		Claire Potter	Commit		commit 103abeda4ccd790ebc937a721c18b8629fb93b50		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add layout changes to menu to improve display. Test changes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add the following styling to the menu to improve display layout width: 80%; / height: 55%; / margin-left: 25px; / padding-top: 10px;		Code entered and saved in stylesheet.css.		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check menu display acroos pages		The menu displays as expected		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_044	Test Case Description		Adjust display for header and footer and test
Created By		Claire Potter	Commit		commit 46d2f3dd733a01fafabea9d1f5af2d6efd60d0a0		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Adjust display for header and footer and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add display changes to Header and Menu to ensure items align as required		Code entered and saved in stylesheet.css		N/A			N/A
2	Change the footer display to flex to improve styling across media queries		Code entered and saved in stylesheet.css		N/A			N/A
3	Adjust media screen widths and font-sizes to improve display		Code removed and saved in stylesheet.css		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check Header and Menu display alignment		Aligned as expected		As Expected			Pass
6	Check the footer display and alignment		Displays and aligns as expected		As Expected			Pass
7	Check header and footer displays across various screen sizes		Header and Footer display as expected		As Expected			Pass
8	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
9	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_045	Test Case Description		Remove @media queries to review and make some display adjustments. Test changes.
Created By		Claire Potter	Commit		commit c04b136f43990d6b1849d6267499ffb1ace93ea2		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Remove @media queries to review and make some display adjustments. Test changes.

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove all media queries from stylesheet to review and add back individually as I am not happy with screen rendering		Code removed and saved in stylesheet.css		N/A			N/A
2	Adjust positioning and alignment for home page display		Code entered and saved in stylesheet.css		N/A			N/A
3	Format and adjust index.html to improve code		Code adjusted and saved in index.html		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check that all media queries are no longer there and content does not adjust to screen size		Content does not adjust to screen sizes		As Expected			Pass
6	Check the home page position and alignment of elements		Home page displays as expected		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_046	Test Case Description		Add @media query for max-width 3072px, 1440px and 1088px and test
Created By		Claire Potter	Commit		commit dd4bedec23e04c231cff8a133bb1a80ad6be37c9		Version		1.0

Tester's Name		Claire Potter	Date Tested		13-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Add @media query for max-width 3072px, 1440px and 1088px and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add max-width 3072px, 1440px and 1088px media queries for index.html		Code entered and saved in css.stylesheet		N/A			N/A
2	Add style adjustments to home-page styling		Code entered and saved in css.stylesheet		N/A			N/A
3	Add z-index to header		Code entered and saved in css.stylesheet		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check the page display across the three screen sizes.		Home page displays as expected and renders well for each screen size.		As Expected			Pass
6	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
7	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_047	Test Case Description		Add style changes to improve readability and visuals and test changes
Created By		Claire Potter	Commit		commit 67843492b3b75c8f44287274b246ee77c4867e7f		Version		1.0

Tester's Name		Claire Potter	Date Tested		14-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Add style changes to improve readability and visuals and test changes

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Set font-size for html as a percentage and change all other font sizes to rem in order to easily change across screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
2	Make background colour for hero text less transparent to improve readability		Code entered and saved in stylesheet.css		N/A			N/A
3	Update learn-more margin for alignment		Code entered and saved in stylesheet.css		N/A			N/A
4	Justify and center Activities section on about.html		Code entered and saved in stylesheet.css		N/A			N/A
5	Update display and layout content for the Hear From Each Other Page		Code entered and saved in stylesheet.css		N/A			N/A
6	Update display for the form on the Contact Us page		Code entered and saved in stylesheet.css		N/A			N/A
7	Add a div for the radio-buttons for style formatting to contact.html		Code entered and saved in contact.html		N/A			N/A
8	Ensure all divs are closed on the Hear from Each Other Page and ensure the feedback and recommendations sections are separate		Code entered and saved in feedback.html		N/A			N/A
9	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
10	Check the font size across different pages to ensure it reflects correctly. Check across screen sizes for media queries added		The font is clearly readable and set at an appropriate size		As Expected			Pass
11	Check the readibility of the text on the home page with the less transparent background		The font is clearly readable and set at an appropriate size		As Expected			Pass
12	Check the alignment of the learn-more button		The learn-more button is aligned with the text		As Expected			Pass
13	Check that the content on the about.html page -Activities - is centered and aligned		Content is centered and aligned as per styling		As Expected			Pass
14	Check the Hear From Each Other Page, that content is displaying as per styling		Content displays as per styling		As Expected			Pass
15	Check the Contact Us Form, that content is displaying as per styling		Content displays as per styling		As Expected			Pass
16	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
17	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_048	Test Case Description		Add media query for max-width 5000px test and save
Created By		Claire Potter	Commit		commit 3fefb038e3415d99fe3f271e17ee8c0cfe77aaed		Version		1.0

Tester's Name		Claire Potter	Date Tested		14-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	about.html preview

Test Scenario	Add media query for max-width 5000px test and save

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add media query styling for screen size max 5000px. Add styling for header, footer, home page, about page, feedback page and contact page.		Code entered and saved in css.stylesheet		N/A			N/A
2	Add small changes to style sheet which had been missed previously		Code entered and saved in css.stylesheet		N/A			N/A
3	Add a feedback-container ID to the div for Feedback and a recommendations-container ID to the div for Recommendations to style		Code entered and saved in feedback.html		N/A			N/A
4	Include styling to the feedback and recommendations IDs in the new media query		Code entered and saved in css.stylesheet		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check all pages for screen size 5000px max to ensure all pages appear sized appropriately and as desired		Pages appear appropriately sized and styled for the screen size.		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_049	Test Case Description		Add media query for max-width 2999px test and save
Created By		Claire Potter	Commit		commit 64837af7c8f62396e041d0b53c9e8e77a0cd3352		Version		1.0

Tester's Name		Claire Potter	Date Tested		14-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	feedback.html preview
3	Utilisation of Code Institute Full Template				3	index.html preview
4					4	about.html preview

Test Scenario	Add media query for max-width 2999px test and save

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add media query styling for screen size max 2999px. Add styling for header, footer, home page, about page, feedback page and contact page.		Code entered and saved in contact.html		N/A			N/A
2	Use Cntrl Alt F to format the stylesheet neatly		Code appears well formatted		N/A			N/A
3	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
4	Check all pages for screen size 2999px max to ensure all pages appear sized appropriately and as desired		All content and styling reflects as wanted for screen size 2999px		As Expected			Pass
5	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
6	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_050	Test Case Description		Add media query for screen max width 2000px and test
Created By		Claire Potter	Commit		commit 1b098e2d6a503660227add12003960371566ef18		Version		1.0

Tester's Name		Claire Potter	Date Tested		14-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	contact.html preview
4					4	feedback.html preview

Test Scenario	Add media query for screen max width 2000px and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add media query styling for screen size max 2000px. Add styling for header, footer, home page, about page, feedback page and contact page.		Code entered and saved in stylesheet.css		N/A			N/A
2	Change max-screen width from 5000 to 6000px		Code entered and saved in stylesheet.css		N/A			N/A
3	Change max-screen width from 2999 to 3000px		Code entered and saved in stylesheet.css		N/A			N/A
4	Add sizing and positioning changes to existing style to improve screen display		Code entered and saved in stylesheet.css		N/A			N/A
5	Complete some spelling corrections and content amendment to feedback.html		Code entered and saved in feedback.html		N/A			N/A
6	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
7	Check all pages for screen size 2000px max to ensure all pages appear sized appropriately and as desired		Pages appear appropriately styled and sized		As Expected			Pass
8	Check all pages for media query sizes to ensure all pages appear sized appropriately and as desired		Pages appear appropriately styled and sized		As Expected			Pass
9	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
10	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## PE051 - PE060
Test Case ID		PE_051	Test Case Description		Use HTML formatter to format pages
Created By		Claire Potter	Commit		commit a86b04977ad355f721556c574a3d337aff134b9e		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Use HTML formatter to format pages

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Copy about.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into about.html		Code removed and formatted and readded to about.html		N/A			N/A
2	Copy contact.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into contact.html		Code removed and formatted and readded to contact.html		N/A			N/A
3	Copy feedback.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into feedback.html		Code removed and formatted and readded to feedback.html		N/A			N/A
4	Copy index.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into index.html		Code removed and formatted and readded to index.html		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the formatting of the html code has not affected the preview of the pages		Site pages appear as expected		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_052	Test Case Description		Use CSS formatter to format CSS
Created By		Claire Potter	Commit		commit f8576cb0d3a5975b368c8a3bf8310effa6778261		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	contact.html preview
4					4	feedback.html preview

Test Scenario	Use CSS formatter to format CSS

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Copy stylesheet.css code and paste into CSS formatter. Once formatted, clear old code and paste formatted code back into stylesheet.css		Code entered and saved in stylesheet.css		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check that the formatting of the css code has not affected the preview of the pages		Pages display with styling as expected		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_053	Test Case Description		Small changes after code validators added and tested
Created By		Claire Potter	Commit		commit 45596660dbe5dd254e384b27fd2dcf046456bd20		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Small changes after code validators added and tested

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add a couple of small changes to the code after the code validator.		Code entered and saved in stylesheet.css. and feedback.html		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check pages have not been affected by the changes apart from spacing added through margins		Pages display with styling as expected		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_054	Test Case Description		Add media query up to width 2400px
Created By		Claire Potter	Commit		commit eb1ae27b764f31a8666d2d07c51a0fc83346200d		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add media query up to width 2400px

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add max-width 2400px media query for all pages		Code entered and saved in stylesheet.css		N/A			N/A
2	Make a couple of width adjustments across media queries		Code entered and saved in stylesheet.css		N/A			N/A
3	Use Cntrl Alt F to format cpde		Code entered and saved in stylesheet.css		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check styling for screens up to 2400px across pages		Displays and fits screen size		As Expected			Pass
6	Check additional changes have impacted screen display positively		Displays and fits screen size		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_055	Test Case Description		Add media query up to width 873px and up to width 1000px
Created By		Claire Potter	Commit		commit de424a454d6410a0c2cb8d3f0cbce130ed1ac3aa		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Add media query up to width 873px and up to width 1000px

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add max-width 1000px media query for all pages		Code entered and saved in stylesheet.css		N/A			N/A
2	Add max-width 873px media query for all pages		Code entered and saved in stylesheet.css		N/A			N/A
3	Make some small style changes to current code for display		Code adjusted and saved in index.html		N/A			N/A
4	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
5	Check that the screen renders correctly for max-width 1000px screens		Content adjusts to screen size		As Expected			Pass
6	Check that the screen renders correctly for max-width 873px screens		Content adjusts to screen size		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_056	Test Case Description		Add media query max width 702px
Created By		Claire Potter	Commit		commit abaca3b57c70f14924ec762f9764c28a7892a669		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	index.html preview
2	Account on Github and Gitpod				2	about.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Add media query max width 702px

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Add max-width 702px media query for all pages		Code entered and saved in stylesheet.css		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check that the screen renders correctly for max-width 702px screens		Content adjusts to screen size		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_057	Test Case Description		Add changes to @media queries while testing display
Created By		Claire Potter	Commit		commit 7d782f3db2376ac8ec4019c8a484a3b3590440f9		Version		1.0

Tester's Name		Claire Potter	Date Tested		16-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	contact.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	index.html preview

Test Scenario	Add changes to @media queries while testing display

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove the float positioning on the profile pictures on the feedback page		Code removed and saved in stylesheet.css		N/A			N/A
2	Remove the solid border and add a margin to the feedback sub section		Code entered and saved in stylesheet.css		N/A			N/A
3	Add a smaller version of the contact page image to only be visible for smaller screen sizes		Code entered and saved in stylesheet.css		N/A			N/A
4	Change the html font size for max screen 702px		Code entered and saved in stylesheet.css		N/A			N/A
5	Update the dropdown content display		Code entered and saved in stylesheet.css		N/A			N/A
6	Update the hero area display		Code entered and saved in stylesheet.css		N/A			N/A
7	Update the hero text display		Code entered and saved in stylesheet.css		N/A			N/A
8	Add the About Page and Contact Page display style to screen max-size 702px		Code entered and saved in stylesheet.css		N/A			N/A
9	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
10	All changes above were made congruently to viewing the preview screens to ensure that the rendered screens dispalyed as wanted		Pages display neatly and clearly for the screen size		As Expected			Pass
11	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
12	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_058	Test Case Description		Continue edit media queries down to width max 300px
Created By		Claire Potter	Commit		commit dbc9291a42eed305cec9fa5da1ff17e2ea134494		Version		1.0

Tester's Name		Claire Potter	Date Tested		17-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	about.html preview

Test Scenario	Continue edit media queries down to width max 300px

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Change home page dispaly to flex to assist with rendering across screen sizes		Code entered and saved in css.stylesheet		N/A			N/A
2	Change max-width from 1000px to max-width: 1044px		Code entered and saved in css.stylesheet		N/A			N/A
3	Change the display for the radio feedback buttons to column for smaller screens		Code entered and saved in css.stylesheet		N/A			N/A
4	Adjust @media screen and (max-width: 873px)		Code entered and saved in css.stylesheet		N/A			N/A
5	Change media query from 702px to 720px		Code entered and saved in css.stylesheet		N/A			N/A
6	Add @media screen and (max-width: 506px)		Code entered and saved in css.stylesheet		N/A			N/A
7	Add @media screen and (max-width: 506px)		Code entered and saved in css.stylesheet		N/A			N/A
8	Add @media screen and (max-width: 300px)		Code entered and saved in css.stylesheet		N/A			N/A
9	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
10	Check all pages across different screen sizes appear sized appropriately and as desired		Pages appear appropriately sized and styled for the screen size.		As Expected			Pass
11	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
12	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_059	Test Case Description		Add final adjustments to media queries
Created By		Claire Potter	Commit		commit 5bd2a195243b75d73f5f2dbed88b6f9d5484e89d		Version		1.0

Tester's Name		Claire Potter	Date Tested		17-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2	feedback.html preview
3	Utilisation of Code Institute Full Template				3	index.html preview
4					4	about.html preview

Test Scenario	Add final adjustments to media queries

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Make required adjustments to stylesheet to ensure all screens render as desired		All content and styling reflects as wanted for screen sizes		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check all pages for screen size to ensure all pages appear sized appropriately and as desired		All content and styling reflects as wanted for screen sizes		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_060	Test Case Description		Fix bottom border on Hear from Each Other
Created By		Claire Potter	Commit		commit 6ebdcfa25bf262ef67bd38107b45e0a52584577f		Version		1.0

Tester's Name		Claire Potter	Date Tested		17-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	feedback.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Fix bottom border on Hear from Each Other

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove the bottom border from the feedback section on Hear from Each Other		Code removed and saved in stylesheet.css		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check that the Hear from Each Other page displays as desired		Page appears appropriately		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## PE061 - PE063
Test Case ID		PE_061	Test Case Description		Add final formatting of code after final validations and test
Created By		Claire Potter	Commit		commit bc26f38954c0134abafe41957d331cb0219eff5b		Version		1.0

Tester's Name		Claire Potter	Date Tested		21-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4

Test Scenario	Add final formatting of code after final validations and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Copy about.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into about.html		Code removed and formatted and readded to about.html		N/A			N/A
2	Copy feedback.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into feedback.html		Code removed and formatted and readded to feedback.html		N/A			N/A
3	Copy index.html code and paste into HTML formatter. Once formatted, clear old code and paste formatted code back into index.html		Code removed and formatted and readded to index.html		N/A			N/A
4	Copy stylesheet.css code and paste into CSS formatter. Once formatted, clear old code and paste formatted code back into stylesheet.css		Code entered and saved in stylesheet.css		N/A			N/A
5	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
6	Check that the formatting of the html code and css code has not affected the preview of the pages		Site pages appear as expected		As Expected			Pass
7	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
8	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_062	Test Case Description		Fix repeat of background at smaller size for contact page and test
Created By		Claire Potter	Commit		commit 98d7d200ffa907a5e594211bb98e0656df775a4a		Version		1.0

Tester's Name		Claire Potter	Date Tested		21-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	contact.html preview
2	Account on Github and Gitpod				2
3	Utilisation of Code Institute Full Template				3
4					4

Test Scenario	Fix repeat of background at smaller size for contact page and test

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	For media query max width 720px change the contact-us-area background to background: none no-repeat		Code entered and saved in stylesheet.css		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Check that the contact-us-area background does not repeat for screens smaller than 720px		Image does not repeat		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass
Test Case ID		PE_063	Test Case Description		Amend the site to meet all accessibility requirements and test through wave tester
Created By		Claire Potter	Commit		commit abcbfdbe91ad043716397d85bdc7a00a8359e7fb		Version		1.0

Tester's Name		Claire Potter	Date Tested		21-May-21		Pass / Fail / Not executed		Pass

S #	Prerequisites:				S #	Test Data
1	Access to Browser				1	about.html preview
2	Account on Github and Gitpod				2	index.html preview
3	Utilisation of Code Institute Full Template				3	feedback.html preview
4					4	contact.html preview

Test Scenario	Amend the site to meet all accessibility requirements and test through wave tester

Step #	Step Details		Expected Results		Actual Results			Pass / Fail / Not executed

1	Remove the link to home page from Header logo as it is a duplicate as it appears next to the Home Navigation link.		Code removed from header logo in all html pages		N/A			N/A
2	Change the colour of the senses sub-heading on What is Sensory Play to #333333 to improve contrast. Remove IDs for individual colours from html.		IDs removed from about.html page. Colour for font changed to #333333 in stylesheet.css		N/A			N/A
3	Change the menu active page text colour from black to white to improve contrast		Code changed in stylesheet.css		N/A			N/A
4	Change the solid-green background to a lighter green for contrast		Code changed in stylesheet.css		N/A			N/A
5	Change all h6 headings to h4 headings in order to not miss headings		Code changed iacross all html pages and stylesheet.css		N/A			N/A
6	Increase the font size of the Footer logo and paragraph for readability		Font size increased in stylesheet.css		N/A			N/A
7	Update the alt image descriptions of the profile pictures on the Hear From Each Other page to be more descriptive		Alt descriptions updated in feedback.html		N/A			N/A
8	Use Cntrl Alt F to ensure pages are still neatly formatted		Code appears neat across all html pages and stylesheet.css		N/A			N/A
2	Open preview browser with python3 -m http.server		Preview browser opens and displays.		As Expected			Pass
3	Use the Wave Evaluation Tool on each site page to ensure it passes all accessibility tests		All pages pass with no errors		As Expected			Pass
4	Add the code to gitpod		Terminal performs without issue.		As Expected			Pass
5	Commit the code to gitpod with message initial commit.		Terminal displays successful commit message.		As Expected			Pass

## User Stories Testing
Primary User
Story	Expected Results	Actual Results	Pass / Fail / Not executed
1. I would like to learn about sensory play in a concise way.	Simple and easy to comprehend content	As expected	Pass
2. I would like to find sensory play activities that engage both of my children.	Relevant activities section with appropriate recommendations for young children	As expected	Pass
3. Information and creative activities that directly address anxiety.	Separate section on anxiety and specific activities to address problem	As expected	Pass
4. I need a site that is straight forward and easy for me to use at home.	Site can be accessed on multiple devices, navigation is intuitive and all content is visible and readable	As expected	Pass
5. Any feedback and recommendations would be useful.	A section which provides feedback and recommendations on the subject of sensory play and on the site itself	As expected	Pass
6. A way to contact the site owner to ask questions, provide feedback and recommendations.	A form that can be submitted which includes the options to ask questions, provide feedback and make recommendations	As expected	Pass

Secondar User One
Story	Expected Results	Actual Results	Pass / Fail / Not executed
1. Easy to utilise resource, can be used by any parent or teacher.	Site can be accessed on multiple devices, navigation is intuitive and all content is visible and readable	As expected	Pass
2. Somewhere I can refer parents to to help their child at home.	Reliable public site	As expected	Pass
3. New ways for parents to include daily activities that engage all five senses; sight, sound, smell, touch and taste.	Relevant activities section with appropriate recommendations for young children which engage all five senses	As expected	Pass
4. Straight forward and affordable activities that can engage multiple children at a time.	Relevant and affordable activities section with appropriate recommendations for young children	As expected	Pass
5. An easy way to hear from other teachers and parents to learn from each other.	A section which provides feedback and recommendations on the subject of sensory play and on the site itself	As expected	Pass

Secondary User Two
Story	Expected Results	Actual Results	Pass / Fail / Not executed
1. A clear direct and educational website educating and advising parents on sensual play.	Simple and easy to comprehend content	As expected	Pass
2. Ability for parents to ask questions.	A form that can be submitted that includes the option to ask questions	As expected	Pass

Secondary User Three
Story	Expected Results	Actual Results	Pass / Fail / Not executed
1. Easy to understand explanation of sensory play.	Simple and easy to comprehend content	As expected	Pass
2. Straight forward and simple activities are a must.	Activities are easy to understand and re-create	As expected	Pass
3. A resource which is intuitive as well as engaging.	Site can be accessed on multiple devices, navigation is intuitive and all content is visible and readable	As expected	Pass